## Totals
Time Estimation And Management Schedule
| GiraldoDario, PAP 1, C201601 |  |  | Project Rate: | 45
Period | Estimate | Actual | Difference
Week1 | 1327.5 | 832.5 | 495
Week2 | 1755 | 1822.5 | -67.5
Week3 | 1980 | 2182.5 | -180
Week4 | 1980 | 2182.5 | -180
| 7042.5 | 7020 | 67.5

## Week1
GiraldoDario PAP 1 C201601
Step | Description | Estimated Time | Actual Time | Time Difference
Week 1
| Embarkation Steps | 3.5 | 1.5 | 2
| Resources For The Journey | 6 | 2 | 4
| Week 1 -Discovery | 20 | 15 | 5
0
0
0
|  | 1327.5 | 832.5 | 495
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Week2
Time Estimation And Management Schedule
GiraldoDario, PAP 1, C201601
Week 2 | Description | Estimated Time | Actual Time | Time Difference
11 - Mon | GoTo Meeting Career Module What Is Portfolio How Do I Create an ePortfolio? Self-Evaluation SWOT -Start | 8 | 6 | 2
12 - Tue | Burn-Up List -Del | 3 | 3 | 0
13 - Wed | SOWT Analysis -Del Anchor Points | 6 |  | 6
14 - Thu | A Call To Action - Failure to Success Story -Del | 9 | 6.5 | 2.5
15 - Fri | Mission Statement | 4 | 8 | -4
16 - Sat | Failure To Success Responses | 5 | 8 | -3
17 - Sun | Project Deliverable | 4 | 9 | -5
|  | 1755 | 1822.5 | -67.5

## Week3
Time Estimation And Management Schedule
GiraldoDario, PAP 1, C201601
Week 3 | Description | Estimated Time | Actual Time | Time Difference
18 - Mon | GoTo Meeting | 12 | 10 | 2
Career Module -Quiz Plus LinkedIn
Communicating With Clarity
Communicating With Visual Tools
19 - Tue | Burn-Up List | 4 | 3 | 1
20 - Wed | Ancor Points | 6 | 4 | 2
21 - Thu | A Call To Action - Encouragement | 7 | 6.5 | 1
22 - Fri | Flowchart | 4 | 8 | -4
23 - Sat | Encouragement Responses | 5 | 8 | -3
24 - Sun | Project Deliverable | 6 | 9 | -3
|  | 1980 | 2182.5 | -180

## Week4
Time Estimation And Management Schedule
GiraldoDario, PAP 1, C201601
Week 4 | Description | Estimated Time | Actual Time | Time Difference
25 - Mon | GoTo Meeting | 12 | 10 | 2
Career Module -Quiz 2/Tasks
26 - Tue | Burn-Up List | 4 | 3 | 1
27 - Wed | Ancor Points | 6 | 4 | 2
28 - Thu | A Call To Action - Growth | 7 | 6.5 | 1
29 - Fri | Time Estimates | 4 | 8 | -4
30 - Sat | Encouragement Responses | 5 | 8 | -3
31 - Sun | Project Deliverable | 6 | 9 | -3
|  | 1980 | 2182.5 | -180